## Gantchart
GANTT CHART | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | IoT Enabled Social Web Framework for Water Consumption Monitoring |  |  |  |  | INSTUTUTE & DEPARTMENT NAME | [6 empty] | A.P Shah Institute of Technology
PROJECT GUIDE |  | Prof. Yaminee Patil |  |  |  |  | DATE | [6 empty] | 2021-02-10
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION(Weeks) | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Research paper search | Nakul,Krutika,Deeksha | 2020-01-20 | 2020-02-08 | 3 | 100% | bar: WEEK 1 F to WEEK 2 T; WEEK 5 M to WEEK 5 F; WEEK 7 M to WEEK 7 F; WEEK 12 M to WEEK 12 F
1.1.1 | Research paper finalization | Nakul,Krutika,Deeksha | 2020-02-08 | 2020-02-26 | 3 | 100% | bar: WEEK 2 W; WEEK 5 M to WEEK 5 F; WEEK 7 M to WEEK 7 F; WEEK 12 M to WEEK 12 F
1.2 | Project Title | Nakul,Krutika,Deeksha | 2020-02-28 | 2020-03-14 | 3 | 100% | bar: WEEK 2 W to WEEK 3 W; WEEK 5 M to WEEK 5 F; WEEK 7 M to WEEK 7 F; WEEK 12 M to WEEK 12 F
1.3 | Abstract | Nakul,Krutika,Deeksha | 2020-03-14 | 2020-03-20 | 1 | 100% | bar: WEEK 2 R to WEEK 3 R; WEEK 5 M to WEEK 5 F; WEEK 7 M to WEEK 7 F; WEEK 12 M to WEEK 12 F
1.4 | Objectives | Nakul,Krutika,Deeksha | 2020-03-21 | 2020-03-27 | 1 | 100% | bar: WEEK 3 M to WEEK 3 R; WEEK 5 M to WEEK 5 F; WEEK 7 M to WEEK 7 F; WEEK 12 M to WEEK 12 F
1.5 | Literature Review | Krutika | 2020-03-28 | 2020-04-03 | 1 | 100% | bar: WEEK 3 T to WEEK 3 R; WEEK 5 M to WEEK 5 F; WEEK 7 M to WEEK 7 F; WEEK 12 M to WEEK 12 F
1.6 | Problem Definition | Nakul | 2020-03-05 | 2020-03-12 | 1 | 100% | bar: WEEK 3 F; WEEK 5 M to WEEK 5 F; WEEK 12 M to WEEK 12 F
1.7 | Scope | Nakul | 2020-03-05 | 2020-03-05 | 1 | 100% | bar: WEEK 3 F; WEEK 5 M to WEEK 5 F
1.8 | Technology stack | Nakul,Krutika,Deeksha | 2020-03-05 | 2020-03-05 | 1 | 100% | bar: WEEK 3 F; WEEK 5 M to WEEK 5 F
1.9 | Benefits for environment | Deeksha | 2020-03-05 | 2020-03-05 | 1 | 100% | bar: WEEK 3 F; WEEK 5 M to WEEK 5 F
1.1 | Benefits for society | Nakul | 2020-03-05 | 2020-03-05 | 1 | 80% | bar: WEEK 3 F; WEEK 5 M to WEEK 5 F
1.11 | Applications | Krutika | 2020-03-05 | 2020-03-05 | 1 | 100% | bar: WEEK 3 F to WEEK 5 F
2 | Project Design
2.1 | Proposed System | Nakul,Krutika | 2020-09-19 | 2020-10-06 | 2 | 85% | bar: WEEK 4 M to WEEK 5 F; WEEK 9 M; WEEK 12 M
2.2 | Design(Flow Of Modules) | Nakul,Krutika,Deeksha | 2020-09-19 | 2020-10-06 | 2 | 100% | bar: WEEK 4 M to WEEK 5 F; WEEK 9 M; WEEK 12 M
2.3 | Activity Diagram | Nakul,Krutika,Deeksha | 2020-09-19 | 2020-10-06 | 2 | 100% | bar: WEEK 4 M to WEEK 5 F; WEEK 9 M; WEEK 12 M
2.4 | Use Case Diagram | Krutika,Deeksha | 2020-09-19 | 2020-10-06 | 2 | 100% | bar: WEEK 4 M to WEEK 5 F; WEEK 9 M; WEEK 12 M
2.5 | Description Of Use Case | Nakul | 2020-09-19 | 2020-10-06 | 2 | 100% | bar: WEEK 5 M to WEEK 6 W; WEEK 9 M; WEEK 12 M
2.6 | Modules | bar: WEEK 5 M to WEEK 6 W; WEEK 9 M; WEEK 12 M
2.6.1 | Module-1 | Krutika,Nakul,Deeksha | 2020-09-19 | 2020-10-06 | 2 | 75% | bar: WEEK 5 M to WEEK 6 W; WEEK 9 M; WEEK 12 M
2.6.2 | Module-2 | Krutika | 2020-09-19 | 2020-10-06 | 2 | 85% | bar: WEEK 5 M to WEEK 6 W; WEEK 9 M; WEEK 12 M
2.6.3 | Module-3 | Nakul | 2020-09-19 | 2020-10-06 | 2 | 85% | bar: WEEK 5 M to WEEK 6 W; WEEK 9 M; WEEK 12 M
2.6.4 | Module-4 | Deeksha | 2020-09-19 | 2020-10-06 | 2 | 85% | bar: WEEK 5 M to WEEK 6 W; WEEK 9 M; WEEK 12 M
2.7 | Preparation Of Report | Krutika | 2020-09-19 | 2021-05-10 | 6 | 100% | bar: WEEK 5 M to WEEK 6 W; WEEK 9 M; WEEK 12 M
3 | Project Implementation
3.1 | Module-1 | Nakul,Krutika,Deeksha | 2020-10-04 | 2020-11-29 | 0 | 100% | bar: WEEK 5 M to WEEK 6 W; WEEK 9 M to WEEK 9 W
3.2 | Module-2 | Nakul | 2020-11-05 | 2021-02-05 | 0 | 100% | bar: WEEK 5 M to WEEK 6 W; WEEK 9 M to WEEK 9 W
3.3 | Module-3 | krutika | 2021-02-05 | 2021-02-12 | 4 | 100% | bar: WEEK 5 M to WEEK 6 W; WEEK 9 M to WEEK 9 W
3.4 | Module-4 | Nakul,Krutika,Deeksha | 2021-02-25 | 2021-02-26 | 4 | 100% | bar: WEEK 5 M to WEEK 6 W; WEEK 9 M to WEEK 9 W
4 | Testing
4.1 | Design of Test Cases | Nakul,Deeksha | 2021-03-03 | 2021-03-09 | 2 | 100% | bar: WEEK 1 T to WEEK 1 F; WEEK 2 T to WEEK 2 F; WEEK 3 T to WEEK 3 F; WEEK 5 M to WEEK 7 M; WEEK 8 M
4.2 | Architecture | Nakul,Krutika,Deeksha | 2021-03-10 | 2021-03-16 | 2 | 90% | bar: WEEK 1 T to WEEK 1 F; WEEK 5 M to WEEK 7 M
4.3 | Prototyping | Nakul,Krutika,Deeksha | 2021-03-17 | 2021-03-23 | 2 | 90% | bar: WEEK 1 T to WEEK 1 F; WEEK 5 M to WEEK 7 M
4.4 | Development | Nakul | 2021-03-24 | 2021-03-30 | 3 | 90% | bar: WEEK 1 T to WEEK 1 F; WEEK 5 M to WEEK 7 M
4.5 | Testing QA | Nakul,Krutika,Deeksha | 2021-03-31 | 2021-04-06 | 5 | 90% | bar: WEEK 1 T to WEEK 1 F; WEEK 5 M to WEEK 7 M
4.6 | Installation of Senser & Meters | Nakul,Krutika | 2021-04-07 | 2021-04-13 | 6 | 60% | bar: WEEK 1 T to WEEK 1 F; WEEK 5 M to WEEK 7 M
4.7 | Configuration Of Dashboard | Nakul | 2021-04-14 | 2021-04-20 | 8 | 90% | bar: WEEK 1 T to WEEK 1 F; WEEK 5 M to WEEK 7 M
4.8 | Worked on wifi module | Krutika | 2021-04-21 | 2021-04-27 | 9 | 40% | bar: WEEK 1 T to WEEK 1 F; WEEK 5 M to WEEK 7 M
4.9 | Connection Of Wifi Module | Deeksha | 2021-04-21 | 2021-04-27 | 9 | 19% | bar: WEEK 1 T to WEEK 1 F; WEEK 5 M to WEEK 7 M
4.1 | Worked on Cloud/csv file | Krutika | 2021-04-28 | 2021-05-04 | 9 | 85% | bar: WEEK 1 T to WEEK 1 F; WEEK 5 M to WEEK 7 M; WEEK 8 M
4.11 | Configuration Of System through which Cloud/csv file will be connected | Nakul,Krutika,Deeksha | 2021-05-05 | 2021-05-11 | 10 | 90% | bar: WEEK 1 T to WEEK 1 F; WEEK 5 M to WEEK 7 M
5 | Results and Analyis
5.1 | Report Preparation | Krutika,Deeksha | 2021-02-25 | 2021-04-26 | 13 | 100% | bar: WEEK 5 W to WEEK 6 F; WEEK 11 M to WEEK 12 M
5.2 | Graphical Representation | Nakul,Krutika,Deeksha | 2021-03-24 | 2021-05-26 | 13 | 90% | bar: WEEK 5 W to WEEK 6 F; WEEK 11 M to WEEK 12 M